## RAID Log
ID | Type (Risk/Issue/Assumption/Dependency) | Description | Impact | Likelihood | Severity | Owner | Mitigation/Next Step | Status | Due Date | Last Updated
R-001 | Risk | NAT Gateway costs may exceed budget due to egress patterns | High | Medium | High | FinOps | Add VPC endpoints; reduce cross-AZ traffic; track weekly | Open | 2026-02-15 | 2026-01-25
I-001 | Issue | Legacy IAM users without MFA remain in prod account | High | Medium | High | Security | Migrate to SSO permission sets; disable keys; enforce MFA | In Progress | 2026-02-05 | 2026-01-25
A-001 | Assumption | RPO of 15 minutes acceptable for analytics workloads | Medium | Low | Medium | Product | Confirm with business; document in HLD | Open | 2026-01-31 | 2026-01-25