## Work Items
Workstream | Task | Complexity (S/M/L) | Est Hours | Role | Notes
Discovery | Discovery workshop + notes | M | 12 | Architect | Includes stakeholder interviews
Assessment | Well-Architected review + findings | M | 20 | Architect | 6 pillars + readout
Security | Enable org trail + baseline guardrails | M | 24 | Security | Depends on org access
FinOps | Tagging policy + budget alerts | S | 12 | FinOps | Quick win
Design | HLD + diagrams | M | 24 | Architect | One primary workload
Design | LLD + IAM/network details | L | 40 | Architect | If multi-account + complex networking
Delivery | CI checks for Terraform (fmt/validate/security scan) | M | 20 | DevOps | GitHub Actions
Handover | Runbooks + KT sessions | M | 16 | Architect | Docs + 2 KT calls

## Summary
Metric | Value
Total Estimated Hours
Estimated Weeks @ 30 hrs/week
Architect Hours
Security Hours
DevOps Hours
FinOps Hours